## TIMELINE
Sprint | Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Project Closure
Dates | 23/01 - 29/01 | 30/01 - 05/02 | 06/02 - 12/02 | 13/02 - 19/02 | 20/02 - 26/02 | 27/02 - 05/03 | 06/03 - 12/03 | 13/03 - 19/03 | 20/03 - 26/03 | 27/03 - 02/04 | 03/04 - 09/04 | 10/04 - 16/04 | 17/04 - 23/04
Week | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15
PLANNED
| Introduction to IHH and Project Brief | First introductory meeting with IHH PX Dept (Jason) | IHH (Pharma Dept) - first meeting to analyse problem statement/KPIs | Develop first prototype of dashboard A | Refine first prototype of Dashboard A | IHH Dept B - first meeting to analyse problem statement/KPIs | Develop first prototype of dashboard B | Refine first prototype of Dashboard B | Develop first prototype of dashboard C | Refine first prototype of Dashboard C | necessary refinements and rapid prototyping of Dashboard C
|  |  | Obtain data for IHH (Pharma Dept) (1 year worth, 4 hospitals, pharm dept) -- Wednesday week 6 | Test first prototype of dashboard A (UAT) | Mid-Term Presentation [24/02] | Obtain data for IHH Dept B from IT Dept | Test first prototype of dashboard B (UAT) | IHH Dept C - first meeting to analyse problem statement/KPIs | Test first prototype of dashboard C (UAT) |  | Final Presentation (Dashboard A, B, C) [07/04]
|  |  | Ideate first prototype of Dashboard A | Generate report from dashboard A and share with IHH Dept A | Finalise Midterm Presentation | Ideate first prototype of Dashboard B | Generate report from dashboard B and share with IHH Dept B | Obtain data for IHH Dept C from IT Dept | Generate report from dashboard B and share with IHH Dept C |  | Debrief/handing over to IHH PX Dept
|  |  |  | Work on Midterm Presentation |  |  |  | Ideate first prototype of Dashboard C
|  |  |  | Obtain IT Structure details from IHH (IT Dept) |  | necessary refinements and rapid prototyping of Dashboard A |  |  | necessary refinements and rapid prototyping of Dashboard B
[6 empty] | Work on automated report generation |  | Test automated report function (UAT) | Refine automated report function
ACTUAL
| Introduction to IHH and Project Brief | First introductory meeting with IHH PX Dept (Jason) | IHH (Pharma Dept) - first meeting to analyse problem statement/KPIs | Meeting with IHH IT department for technical requirements | Mid-Term Presentation [24/02] | Ideate first prototype of Pharmacy Dashboard | Official agreement with IHH PX Team to drop departments C and D | Refine first prototype of Call Centre Dashboard |  | Review of Pharmacy Dashboard with IHH PX Team [29/03] | Call Centre UAT Test | Review of Pharmacy Dashboard with IHH Pharmacy Team & all relevant stakeholders [14/04] | Debrief/Handover to IHH PX Dept
|  |  |  | Obtain data for IHH (Pharma Dept) | IHH Call Centre Department - first meeting to analyse problem statement/KPIs | Ideate first prototype of Call Centre Dashboard | Develop first prototype of Call Centre Dashboard |  |  | Refine first prototype of Pharmacy Dashboard |  | Refine second prototype of Pharmacy Dashboard | Submission of ALL Project Collaterals [21/04]
|  |  |  | Work on Midterm Presentation | Obtain data for IHH (Call Centre Dept) |  | Review of Call Centre Dashboard with IHH PX Team [12/03] |  |  | Second Review of Call Centre Dashboard with IHH Call Centre Team & all relevant stakeholders [01/04] | Final Presentation (Call Centre and Pharmacy Dashboard) [07/04] | Pharmacy UAT Test
[5 empty] | Data cleaning and synthesising - Call Centre Dashboard | In-depth Data Analysis - Call Centre Dashboard | Develop first prototype of Pharmacy Dashboard |  |  | Refine second prototype of Call Centre Dashboard |  | Documentation of 3 User Guides - Backend Analysis, Power BI Dashboard, Dashboard Business Users
|  |  |  | Data cleaning and synthesising - Pharmacy Dashboard | [5 empty] | Work on Final Presentation | Development of Poster
In-depth Data Analysis - Pharmacy Dashboard