## Sheet1
23/01 - 29/01 | 30/01 - 05/02 | 06/02 - 12/02 | 13/02 - 19/02 | 20/02 - 26/02 | 27/02 - 05/03 | 06/03 - 12/03 | 13/03 - 19/03 | 20/03 - 26/03 | 27/03 - 02/04 | 03/04 - 09/04
week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13
Introduction to IHH and Project Brief | First introductory meeting with IHH PX Dept (Jason) | IHH Dept A - first meeting to analyse problem statement/KPIs | Develop first prototype of dashboard A | Refine first prototype of Dashboard A | IHH Dept B - first meeting to analyse problem statement/KPIs | Develop first prototype of dashboard B | Refine first prototype of Dashboard B | Develop first prototype of dashboard C | Refine first prototype of Dashboard C | necessary refinements and rapid prototyping of Dashboard C
|  | Obtain data for IHH Dept A from IT Dept | Test first prototype of dashboard A (UAT) | Mid-Term Presentation (Dashboard A) [24/02] | Obtain data for IHH Dept B from IT Dept | Test first prototype of dashboard B (UAT) | IHH Dept C - first meeting to analyse problem statement/KPIs | Test first prototype of dashboard C (UAT) |  | Final Presentation (Dashboard A, B, C) [07/04]
|  | Ideate first prototype of Dashboard A | Generate report from dashboard A and share with IHH Dept A |  | Ideate first prototype of Dashboard B | Generate report from dashboard B and share with IHH Dept B | Obtain data for IHH Dept C from IT Dept | Generate report from dashboard B and share with IHH Dept C |  | Debrief/handing over to IHH PX Dept
Ideate first prototype of Dashboard C
[5 empty] | necessary refinements and rapid prototyping of Dashboard A |  |  | necessary refinements and rapid prototyping of Dashboard B
[5 empty] | Work on automated report generation |  | Test automated report function (UAT) | Refine automated report function